## Datenerfassung
Datum | Dauer [hh:mm] | Primäre Tätigkeit | Anmerkung
2021-03-01 | 2:00 | LV-Einheit | Teilnahme an Vorbesprechung
2021-03-07 | 0:40 | Softwarekonzept | Team Meeting
2021-03-08 | 1:20 | LV-Einheit | Team Meeting, now with full team + find regular spot for jour fixe
2021-03-12 | 3:45 | Softwarekonzept | formulation
2021-03-14 07:12 | 1:00 | Softwarekonzept | Componentdiagram
2021-03-16 | 1:35 | Koordination und Projektmanagement | Discuss Softwareconcept in Team
2021-03-18 | 1:30 | Softwarekonzept | Format Word Document and include team feddback
2021-03-22 | 1:30 | LV-Einheit | Proseminar
2021-03-25 | 0:30 | Koordination und Projektmanagement | Planning next steps
2021-03-27 | 6:30 | Implementierung | Init frontend & project, mainly adjusting skeleton
2020-03-28 | 0:50 | Software/System Design und Architektur | Adjusting SW-Architecture to feedback
2021-03-28 | 1:00 | Koordination und Projektmanagement | team meeting
2021-04-09 | 5:00 | Implementierung | User API
2021-04-10 | 9:00 | Implementierung | User API
2021-04-10 | 1:00 | Koordination und Projektmanagement | Team Meeting
2021-02-11 | 3:00 | Implementierung | User API & lokales DB Setup
2021-02-11 | 9:00 | Tests | User API Tests & Anpassung an andere Commits
2021-04-16 | 0:30 | Koordination und Projektmanagement | backend team meeting
2021-04-16 | 0:30 | Koordination und Projektmanagement | adjusting git issues
2021-04-16 | 7:00 | Implementierung | User API Update for easier implementation in frontend, also adopting tests
2021-04-16 | 0:30 | Koordination und Projektmanagement | team meeting
2021-04-17 | 1:30 | Implementierung | supporting team mates with User API and Topic API
2021-04-19 | 0:30 | Koordination und Projektmanagement | team meeting
2021-04-23 | 3:00 | Tests | UserConrollerTest and fixes to user serives
2021-04-24 | 7:30 | Tests | UserControllerTest and small UserServiceFixes
2021-04-29 | 4:00 | Tests | finishing UserControllerTest
2021-04-30 | 0:30 | Koordination und Projektmanagement | JourFixe
2021-05-01 | 3:00 | Tests | TeamRepositoryTests / Team implementation, pair programming
2021-05-02 | 5:30 | Implementierung | Room Backend Implementation
2021-05-03 | 0:30 | Implementierung | Room Backend Implementation
2021-05-03 | 0:30 | Koordination und Projektmanagement | JourFixe
2021-05-04 | 1:30 | Implementierung | Room Backend Implementation
2021-05-06 | 0:30 | Koordination und Projektmanagement | Backend Meeting
2021-05-06 | 3:00 | Implementierung | Room Backend Implementation
2021-05-07 | 6:00 | Implementierung | Room Backend Implementation
2021-05-07 | 1:00 | Koordination und Projektmanagement | Backend Meeting
2021-05-08 | 6:00 | Implementierung | Room Backend Implementation
2021-05-08 | 1:00 | Implementierung | Support Cube Implementation
2021-05-09 | 3:00 | Implementierung | Room Backend Implementation
2021-05-09 | 1:00 | Implementierung | Support Cube Implementation
2021-05-09 | 4:00 | Implementierung | Room Overview Frontend Implementation
2021-05-10 | 7:30 | Implementierung | Room View Frontend
2021-05-10 | 1:30 | LV-Einheit | Proseminar
2021-05-11 | 5:00 | Koordination und Projektmanagement | Review and Bugfix Game Backend Merge Request
2021-05-11 | 2:00 | Implementierung | Room View Frontend
2021-05-12 | 11:30 | Implementierung | Room View Frontend
2021-05-13 | 3:00 | Implementierung | Room View Frontend
2021-05-13 | 11:00 | Implementierung | Game View Frontend, at the end searching for a major bakend bug
2021-05-14 | 5:00 | Implementierung | Bug Fixing in Backend Game
2021-05-15 | 5:00 | Implementierung | Suppoirt Frontend Game View
2021-05-16 | 3:00 | Implementierung | Support final bug fixing
2021-05-20 | 2:30 | Systemtest (fremdes System) | Fixing and combining prework from team.
2021-05-28 | 2:45 | Koordination und Projektmanagement | Meeting to react to feedback by creating git issues and summerizing in a file. 45min Prep time included.
2021-05-31 | 1:30 | LV-Einheit | Proseminar
2021-06-07 | 5:00 | Koordination und Projektmanagement | Meeting
2021-06-10 | 0:40 | Implementierung | Trying to confirm an issue
2021-06-10 | 1:45 | Implementierung | Room Improvement
2021-06-11 | 3:20 | Implementierung | Room Improvement, Improve Room and Game Leaving Reliability
2021-06-11 | 0:30 | Koordination und Projektmanagement | Meeting
2021-06-12 | 6:00 | Implementierung | Improve Room and Game Leaving Reliability
2021-06-13 | 3:15 | Implementierung | Improve Room and Game Leaving Reliability
2021-06-13 | 0:30 | Koordination und Projektmanagement | Write down times and manage git issues / create MR
2021-06-14 | 2:30 |  | Prepare Proseminar Presentation
2021-06-14 | 1:00 | LV-Einheit | Proseminar
2021-06-14 | 1:00 | Implementierung | Remove (Virtual) Users in Room
2021-06-14 | 0:45 | Koordination und Projektmanagement | Meeting to plan "Abschlussbericht"
2021-06-14 | 1:00 | Abschlussbericht
2021-06-15 | 2:00 | Abschlussbericht
2021-06-15 | 0:25 | Implementierung | Clean up and Adopt MR Suggestions for Improve Room and Game Leaving Reliability
2021-06-15 | 1:00 | Implementierung | Remove (Virtual) Users in Room
2021-06-16 | 4:30 | Implementierung | Remove (Virtual) Users in Room
2021-06-17 | 0:40 | Abschlussbericht | Read and Comment Contributions by teammates
2021-06-17 | 3:30 | Implementierung | Spectate Feature
2021-06-17 | 0:40 | Koordination und Projektmanagement | Update Timemanagment
2021-06-17 | 1:00 | Koordination und Projektmanagement | Meeting
2021-06-18 | 0:30 | Implementierung | Clean Up
2021-06-18 | 0:30 | Koordination und Projektmanagement | Review Cube MR

## Tätigkeiten
ID | Bezeichnung
0 | LV-Einheit
1 | Softwarekonzept
2 | Systemtest (fremdes System)
3 | Abschlussbericht
4 | Abschlusspräsentation
11 | Einarbeitung, Dokumentation lesen
12 | Software/System Design und Architektur
13 | Implementierung
14 | Tests
15 | Konfiguration und Deployment
16 | Koordination und Projektmanagement